Sprint 2 Retrospective — All Teams

Date: January 31, 2026 (Friday) | 4:00 PM - 5:00 PM IST

Facilitator: Priya Sharma, VP Engineering

Attendees: All engineering team leads, Sarah Chen, James Rodriguez, Aisha Patel, Raj Krishnan

What Went Well

Platform Team (Raj)

Data API v2 shipped on time (January 31) — first major launch delivered on schedule in 3 sprints

Performance exceeds targets: 89ms average response (target was 150ms)

67 customers migrated in first 10 days with zero support escalations

Documentation quality praised by 3 partner developers

AI/ML Team (Rachel)

Lead Scoring real-time API complete: 145ms average latency

Model AUC holding at 0.87 on validation; early production data shows 0.85

Hybrid approach working as designed — lightweight model catches 91% of "hot" leads instantly

Product-Support Team (James)

Twitter/X integration shipped clean — zero P1 bugs

WhatsApp integration complete despite initial Business API setup challenges

Security Team

SSO/SAML shipped January 30 — immediately unblocked 3 Enterprise deals

SOC 2 audit progressing on schedule

What Didn't Go Well

Product-Support Team (James)

WhatsApp took 7 extra story points due to undocumented API behaviors

Velocity was 55 vs planned 62 — capacity planning was optimistic for new integrations

Flag: Facebook/Instagram integration (next sprint) will face similar Meta API challenges. Already discovered rate limiting issue that requires architecture pivot from polling to webhooks.

Product-Sales Team

Lead Scoring mobile design wasn't finalized going into sprint — caused 3 points of carry-over

Coordination with Lisa's design team needs improvement: design handoffs happening mid-sprint, not pre-sprint

Platform Team (Raj)

API v2 pagination bug found on launch day — cursor not working for custom objects

Root cause: Custom objects have composite keys vs. simple auto-increment IDs. Edge case missed in testing.

Hotfix shipping Feb 12.

General

Sprint 2 aggregate velocity: 297 points vs 314 planned = 95% delivery rate. Acceptable but below our 97% Q4 average.

Decisions Made During Retro

| Decision | Context |
| --- | --- |
| Design handoffs must complete 3 days before sprint start | Prevents mid-sprint design changes that disrupt velocity |
| Meta integrations (FB/Instagram) to use webhook architecture | Polling approach won't scale beyond 100 customers. James estimated 2-week delay. Priya approved. |
| API v2 custom object testing to be added to regression suite | Prevents similar edge cases in future API work |

Action Items

| Action | Owner | Due |
| --- | --- | --- |
| Complete mobile design for Lead Scoring by Feb 17 | Lisa Park | Feb 17 |
| Implement Meta webhook infrastructure | James + 1 backend engineer | Feb 14 |
| Add custom object pagination tests to CI | Raj Krishnan | Feb 7 |
| Update sprint planning template to include design readiness check | Priya Sharma | Feb 3 |
| Present Unified Inbox v2 delay risk to Sarah for stakeholder communication | James Rodriguez | Feb 3 |

Team Health Check (Anonymous Poll)

| Question | Score (1-5) | Trend |
| --- | --- | --- |
| I'm proud of what we shipped | 4.2 | Up from 3.8 |
| I have clarity on priorities | 4.0 | Stable |
| Cross-team collaboration is effective | 3.4 | Down from 3.7 |
| I feel sustainable pace | 3.1 | Down from 3.5 |

Priya's note: Sustainable pace declining is a concern. With Q1 being our heaviest shipping quarter, we need to watch for burnout. Proposing a team wellness day in March after beta launches.