## Slide 1
Product Launch Plan
AI Lead Scoring Engine — NexusCRM
Sarah Chen, Head of Product | February 2026

## Slide 2
Launch Summary
Feature: AI-Powered Lead Scoring with Explainability
Beta: March 15, 2026 | GA: May 1, 2026
Target: 200 customers activated in first 90 days
• Segment: Enterprise & Mid-Market (Pro tier+)
• Pricing: Included in Pro ($89/user/month) and Enterprise ($149/user/month)
• Beta: 20 hand-selected Enterprise accounts
• Key Metric: Lead-to-opportunity conversion improvement >= 25%

## Slide 3
Pre-Launch Checklist
Engineering (Priya Sharma)
• ✅ Core scoring model trained (AUC: 0.87)
• ✅ Real-time scoring API (< 200ms p99)
• ☐ Score display in list view + mobile — Due Feb 28
• ☐ Explainability panel (SHAP) — Due Mar 5
• ☐ Load testing at 10x volume — Due Mar 12
Marketing (Nina Kowalski)
• ☐ Blog post + demo video — Due Mar 10-12
• ☐ Webinar scheduled Apr 3
• ☐ Competitive battle card vs Salesforce Einstein — Due Mar 1

## Slide 4
Beta Program
Confirmed Beta Customers
• TechFlow Inc. — 2,400 leads/month, VP Sales championing
• CloudBase Corp — 1,800 leads/month, already using Zapier scoring
• DataBridge Inc. — 900 leads/month, requested AI in Q3
• GrowthStack — 1,200 leads/month, high engagement
• SaaSMetrics Inc. — 3,100 leads/month, board connection
+ 15 more to be confirmed by Feb 15
Beta Success Criteria
• Model accuracy (AUC) >= 0.82
• Latency < 500ms p95
• 90% beta customer activation
• 70% weekly active usage
• Satisfaction >= 4.0/5

## Slide 5
Risk Register
• Model accuracy below target on real data — Mitigation: AI + rule-based hybrid fallback
• Insufficient customer training data — Mitigation: 500 lead minimum; synthetic augmentation
• Salesforce competes before our GA — Mitigation: Explainability (SHAP) is our differentiator
• EU privacy/GDPR concerns — Mitigation: In-region processing; no PII in model features

## Slide 6
Post-Launch Measurement
Week 1-2: Technical Stability
• Error rate < 0.1%, Latency within SLA, No P1 bugs
Month 1: Adoption
• 200 customers activated, 80% daily active usage
Month 3: Impact
• Conversion improvement >= 25%, Feature NPS >= 50, 3 case studies
Month 6: Business Impact
$1.2M incremental ARR attributed to AI features
• 10 competitive wins where AI scoring was deciding factor