## Slide 1
Quarterly Business Review — Q4 2025
NexusCRM Product Update
Sarah Chen, Head of Product | January 8, 2026

## Slide 2
Q4 2025 Scorecard
Features Shipped: 14 (Target: 12) ✅
On-Time Delivery: 73% (Target: 80%) ⚠️
P1/P2 Bugs to Prod: 8 (Target: <5) ❌
Feature NPS: 52 (Target: 45) ✅
Engineering Velocity: 298 pts/sprint (Target: 320) ⚠️
Strong feature output but quality and timeliness need improvement. Unified Inbox rush introduced 5 P1 bugs.

## Slide 3
Key Launches in Q4
Unified Inbox v1 (Shipped Nov 15)
• 85 customers activated in first 6 weeks
• Support ticket volume reduced 18% for activated customers
• Issue: 5 P1 bugs in first week — hotfixed within 48 hours
Real-time Notification System (Shipped Oct 20)
• 92% of active users opted in
• Reduced time to awareness from 4 hours to 3 minutes
Data API v1 (Shipped Dec 1)
• 45 customers generating API traffic in first month
• Average 12,000 API calls/day

## Slide 4
What Didn't Ship (and Why)
AI Lead Scoring Beta → Delayed to March 2026
• Data pipeline dependencies took 6 weeks longer than estimated
• ML team pulled to fix recommendation engine issues
Custom Dashboard Builder → Delayed to March 2026
• Deprioritized when Unified Inbox timeline expanded
• Design team bandwidth constrained
Decision (Nov 8): Delayed Lead Scoring & Dashboards to ensure Unified Inbox quality. Inbox was blocking 3 Enterprise renewals worth $420K combined.

## Slide 5
Customer Feedback Themes
Top 5 Feature Requests (Q4 survey, n=312)
#1 Custom Dashboards — 72% of respondents
#2 Workflow Automation — 68% (new entry)
#3 AI Lead Scoring — 54%
#4 Better Mobile Experience — 41% (improving)
#5 Reporting/Export — 38%
NPS by Segment
• Enterprise: 48 → 55 (Unified Inbox impact)
• Mid-Market: 42 → 44 (Stable)
• SMB: 38 → 35 (Declining — pricing concerns)

## Slide 6
Q1 2026 Plan
1. AI Lead Scoring Engine — Beta March 15 (Sarah Chen)
2. Unified Inbox v2 — Social Channels + AI (James Rodriguez)
3. Custom Dashboard Builder — Beta March 30 (Aisha Patel)
4. Data API v2 — Ship January 31 (Raj Krishnan)
5. SOC 2 Type II — Complete March 15 (Security)
Resource Allocation
• 40% AI/ML initiatives
• 30% Unified CX (Inbox + Dashboards)
• 20% Platform (API, Marketplace prep)
• 10% Infrastructure (SOC 2, performance)

## Slide 7
Asks & Discussion
• Headcount: Requesting 2 ML engineers — need recruiter support
• Budget: $50K for Vertex AI compute costs in Q1
• Decision needed: Pursue HIPAA compliance in 2026? 3 prospects worth $800K but $200K investment required
• Risk flag: Salesforce launched Einstein Lead Scoring v3 with real-time. Our beta is 3 months away.