Monthly Stakeholder Update — February 2026

From: Sarah Chen, Head of Product

To: Executive Team, Engineering Leads, Sales Leadership

Date: February 10, 2026

Executive Summary

Good progress across all Q1 initiatives. Data API v2 shipped on time. AI Lead Scoring is on track for March beta. Dashboard Builder design phase complete. One flag: Unified Inbox social channel integration hitting rate limiting issues with Meta's API — potential 2-week delay.

Initiative Status

1. AI Lead Scoring Engine

Status: On Track | Owner: Sarah Chen | Target: March 15 beta

Model performance: AUC 0.87 on validation set (above 0.85 target)

Real-time scoring API complete: 145ms average latency (target < 200ms)

12 of 20 beta customers confirmed; outreach to remaining 8 in progress

Blocker resolved: Data pipeline delay from Q4 fixed. Training pipeline now runs weekly.

Next 2 weeks: Complete explainability panel UI, begin load testing

2. Unified Inbox v2 — Social Channels

Status: At Risk (2 weeks) | Owner: James Rodriguez | Target: Feb 28 → Mar 14

Twitter/X integration complete and tested

WhatsApp Business API integration complete

Issue: Facebook Messenger and Instagram integration hitting Meta Graph API rate limits. Our approach of polling for new messages doesn't scale beyond 100 customers. Need to migrate to Meta Webhooks.

Decision needed: Accept 2-week delay to implement webhook approach (recommended) or ship without Facebook/Instagram and add later?

James's recommendation: Take the 2-week delay. Facebook Messenger is the #2 requested social channel (after WhatsApp). Shipping without it undermines the "unified" promise.

3. Custom Dashboard Builder

Status: On Track | Owner: Aisha Patel | Target: March 30 beta

Design phase complete: All 8 widget types designed and reviewed

Engineering sprint 1 of 6 complete (widget rendering engine)

Data API v2 dependency resolved (shipped Jan 31)

Risk: Permissions framework update from security team slipped to Feb 22 (was Feb 15). 1-week buffer remains.

4. Data API v2

Status: Shipped | Owner: Raj Krishnan | Shipped: January 31

Launched on schedule

67 customers migrated from v1 in first 10 days

Performance: Average response time 89ms (target < 150ms)

One minor issue: Pagination cursor not working for custom objects. Hotfix in progress, shipping Feb 12.

v1 deprecation notice sent: Sunset date June 30, 2026.

5. SOC 2 Type II

Status: On Track | Owner: Security Team | Target: March 15

Audit in progress with Deloitte

2 minor findings so far (logging gaps in admin actions, MFA not enforced for API tokens)

Remediation in progress — estimated 1 week each

No blockers to March 15 completion

Key Decisions This Month

| Decision | Date | Participants | Outcome |
| --- | --- | --- | --- |
| Beta customer selection for AI Lead Scoring | Feb 3 | Sarah, David Kim, Rachel Torres | Selected 20 accounts based on data volume, engagement, and willingness to provide feedback |
| PDF rendering library for Dashboard exports | Feb 5 | Aisha, Engineering | Chose Playwright over Puppeteer — better stability and CSS grid rendering |
| Webhook authentication for Workflow Engine | Feb 7 | Marcus Webb, Security | API keys for Phase 1; OAuth2 in Phase 2. Simplifies initial implementation by 3 weeks. |

Customer Signals

Wins

CloudNet Global renewed at $180K ARR (up from $120K) — cited Unified Inbox as primary reason

TechFlow Inc. agreed to be AI Lead Scoring beta reference customer

3 new Enterprise prospects in pipeline specifically requesting AI features ($350K combined)

Losses / At-Risk

FinanceFlow ($95K ARR) evaluating Salesforce — they need custom dashboards NOW. Dashboard Builder beta in March may be too late. David Kim proposing early access.

RetailMax ($62K ARR) churned — cited lack of workflow automation. "We switched to HubSpot because they have native workflows and we were tired of maintaining 18 Zapier integrations."

Feature Requests Trending Up

Workflow automation (urgency increasing — RetailMax churn is a signal)

Multi-currency support for APAC expansion

AI email drafting for sales outreach

Asks

Engineering support: Need 1 backend engineer to help James on Meta webhook migration (2-week assignment)

Budget approval: $12K for Playwright license (Dashboard PDF rendering)

Alignment: Can we offer FinanceFlow early beta access to Dashboard Builder to prevent churn? Need Sales + Product alignment by Feb 14.