NexusCRM Product Roadmap — Q1-Q2 2026

Owner: Sarah Chen, Head of Product

Last Updated: January 20, 2026

Status: Board Approved

Strategic Themes

Theme 1: AI-First CRM (40% of engineering investment)

Transform NexusCRM from a system of record to a system of intelligence. Every surface should have AI assistance.

Theme 2: Unified Customer Experience (30%)

Break down silos between sales, support, and marketing modules. Customers interact with brands as one entity — our product should reflect that.

Theme 3: Platform & Extensibility (20%)

Make NexusCRM the platform others build on. Marketplace, APIs, and developer tools.

Theme 4: Scale & Reliability (10%)

Infrastructure investments for 10x growth. Multi-region, performance, security.

Q1 2026 (January - March)

NOW — In Development

| Initiative | Owner | Status | Target Ship | Revenue Impact |
| --- | --- | --- | --- | --- |
| AI Lead Scoring Engine | Sarah Chen | Dev Sprint 3/8 | March 15 | $1.2M ARR uplift |
| Unified Inbox - Social Channels | James Rodriguez | Dev Sprint 5/6 | Feb 28 | Churn prevention ($800K) |
| Custom Dashboard Builder | Aisha Patel | Design Complete, Dev Starting | March 30 | $2.8M churn prevention |
| Data API v2 | Raj Krishnan | Beta Testing | Jan 31 | Platform dependency |
| SOC 2 Type II Audit | Security Team | In Progress | March 15 | Enterprise requirement |

Key Milestones - Q1

Jan 31: Data API v2 ships (unblocks Dashboard Builder)

Feb 15: Unified Inbox social channels beta with 10 customers

Feb 28: Unified Inbox GA

Mar 1: AI Lead Scoring beta launch (20 Enterprise customers)

Mar 15: SOC 2 Type II certification complete

Mar 30: Dashboard Builder beta

Q2 2026 (April - June)

NEXT — Planned

| Initiative | Owner | Status | Target Ship | Revenue Impact |
| --- | --- | --- | --- | --- |
| Workflow Automation Engine | Sarah Chen / Marcus Webb | PRD Under Review | May 15 | $1.8M new ARR |
| AI Lead Scoring - GA | Sarah Chen | Pending beta results | May 1 | Included above |
| Dashboard Builder - GA | Aisha Patel | Pending beta | April 30 | Included above |
| Mobile App Redesign | Lisa Park | Design Phase | June 15 | Retention improvement |
| Unified Inbox - AI Replies | James Rodriguez | Research | June 1 | Support efficiency |
| Marketplace v1 | Platform Team | Architecture | June 30 | Ecosystem play |

Key Milestones - Q2

Apr 15: Dashboard Builder GA release

May 1: AI Lead Scoring GA + performance dashboard

May 15: Workflow Automation beta (50 customers)

Jun 1: Unified Inbox AI replies beta

Jun 15: Mobile app redesign rollout

Jun 30: Marketplace beta with 10 partner integrations

H2 2026 — LATER (Directional, Not Committed)

| Initiative | Theme | Confidence | Notes |
| --- | --- | --- | --- |
| AI Workflow Generation | AI-First | Medium | Natural language to workflow. Depends on automation engine adoption. |
| Customer 360 View | Unified CX | High | Single view merging sales, support, marketing data per account. |
| Predictive Churn Model | AI-First | Medium | Requires 12+ months of customer health data. |
| Multi-region Deployment (EU) | Scale | High | GDPR requirement for EU enterprise expansion. |
| Advanced Reporting & BI | Platform | Low | May partner instead of build. Evaluating Metabase embed. |
| Conversation Intelligence | AI-First | Low | Call recording analysis. Highly competitive market. |

Resource Allocation

| Team | Q1 Focus | Q2 Focus | Headcount |
| --- | --- | --- | --- |
| AI/ML Team | Lead Scoring | Workflow AI + Inbox AI | 6 engineers + 2 data scientists |
| Platform Team | Data API v2 | Marketplace + Scale | 8 engineers |
| Product Team (Sales) | Lead Scoring + Dashboards | Workflow Engine | 4 engineers + 1 designer |
| Product Team (Support) | Unified Inbox | Inbox AI + Analytics | 5 engineers + 1 designer |
| Mobile Team | Bug fixes, maintenance | Full redesign | 3 engineers + 1 designer |
| Security | SOC 2, Permissions | Multi-region prep | 2 engineers |

Total Engineering: 28 engineers, 4 designers, 2 data scientists

Decision Log (Roadmap-Level)

| Date | Decision | Context | Made By |
| --- | --- | --- | --- |
| Dec 15, 2025 | Prioritize Workflow Automation over Customer 360 in Q2 | Customer 360 requires data unification work not ready until H2. Workflows have clearer revenue case ($1.8M). | Sarah Chen + Amanda Liu (CEO) |
| Dec 10, 2025 | Delay mobile redesign from Q1 to Q2 | Mobile usage is only 12% of total. Dashboard builder has higher ROI. | Product Leadership |
| Nov 28, 2025 | SOC 2 Type II is Q1 blocker | 3 Enterprise deals ($1.4M combined) contingent on certification. Non-negotiable. | David Kim (VP Sales) + Amanda Liu |
| Nov 15, 2025 | Reject Conversation Intelligence for 2026 | Market too competitive (Gong, Chorus). Focus on CRM-native AI instead. | Marcus Webb (CTO) |

Risks & Dependencies

| Risk | Mitigation | Owner |
| --- | --- | --- |
| Data API v2 delays block Dashboard Builder | Weekly syncs between Platform and Product teams. Fallback: use existing API with degraded performance. | Raj Krishnan |
| Lead Scoring beta shows < 0.80 AUC | Extending beta by 4 weeks; backup plan with rule-based scoring hybrid. | Rachel Torres |
| SOC 2 audit findings require remediation | Security team has 4-week buffer built into timeline. | Security Lead |
| Workflow engine scope creep (AI generation pressure from Sales) | AI generation explicitly Phase 2. CEO aligned. | Sarah Chen |