## RICE Prioritization
NexusCRM Feature Prioritization — RICE Scoring (Q1 2026)
Owner: Sarah Chen, Head of Product ¦ Last Updated: January 20, 2026
Feature | Epic ID | Reach (users/quarter) | Impact (1-3) | Confidence (%) | Effort (person-weeks) | RICE Score | Priority Rank | Status | Owner | Notes
AI Lead Scoring Engine | NEXUS-4521 | 4200 | 3 | 85 | 24 | 446 | 1 | In Development | Sarah Chen | Beta launch March 15. AUC 0.87 validated.
Unified Inbox Social Channels | NEXUS-5102 | 3800 | 3 | 90 | 18 | 570 | 2 | In Development | James Rodriguez | Meta API rate limiting issue being resolved.
Custom Dashboard Builder | NEXUS-6200 | 5100 | 3 | 80 | 30 | 408 | 3 | Design Complete | Aisha Patel | Blocked on Data API v2 (shipped Jan 31). Now unblocked.
Workflow Automation Engine | NEXUS-7800 | 4500 | 3 | 70 | 32 | 296 | 4 | PRD Review | Sarah Chen / Marcus Webb | Q2 target. CEO aligned on no-code first approach.
Mobile App Redesign | NEXUS-8100 | 1800 | 2 | 75 | 20 | 135 | 5 | Design Phase | Lisa Park | Q2 target. Mobile usage 12% - lower ROI than other initiatives.
AI Reply Suggestions (Inbox) | NEXUS-5200 | 2200 | 2 | 60 | 16 | 165 | 6 | Research | James Rodriguez | Depends on Unified Inbox v2 completion. Q2 target.
Marketplace v1 | NEXUS-9000 | 800 | 2 | 50 | 24 | 33 | 7 | Architecture | Platform Team | Long-term ecosystem play. Q2-Q3 timeline.
SSO/SAML Support | NEXUS-3300 | 3200 | 1 | 95 | 6 | 507 | 8 | Development | Security Team | Shipping Jan 30. 3 Enterprise deals contingent.
Customer 360 View | NEXUS-8500 | 3400 | 3 | 40 | 28 | 146 | 9 | Backlog | TBD | Requires data unification not ready until H2.
Conversation Intelligence | NEXUS-8800 | 1200 | 2 | 30 | 36 | 20 | 10 | Rejected for 2026 | N/A | Market too competitive (Gong Chorus Clari). CTO decision Nov 2025.
Multi-currency Support | NEXUS-7200 | 900 | 2 | 80 | 8 | 180 | 11 | Backlog | Platform Team | Needed for APAC expansion. 5 customer requests.
Advanced Reporting Export | NEXUS-6500 | 2800 | 1 | 70 | 12 | 163 | 12 | Backlog | Aisha Patel | Partially addressed by Dashboard Builder.
Bulk Data Import Tool | NEXUS-4800 | 1500 | 1 | 90 | 4 | 338 | 13 | Backlog | Platform Team | Quick win for onboarding improvement.
Email Sequence Automation | NEXUS-7850 | 2100 | 2 | 65 | 14 | 195 | 14 | Backlog | James Rodriguez | Subset of Workflow Engine. May ship as part of NEXUS-7800.
Custom Object Relationships | NEXUS-6100 | 1800 | 2 | 75 | 10 | 270 | 15 | Backlog | Raj Krishnan | API v2 enables this. Q3 candidate.

## Summary
RICE Scoring Summary
RICE Formula:
RICE Score = (Reach x Impact x Confidence) / Effort
Impact Scale:
3 = Massive (>2x improvement)
2 = High (notable improvement)
1 = Low (minimal improvement)
Status Legend:
In Development
Design/Review
Backlog
Rejected