## Sprint Capacity
NexusCRM Sprint Capacity Planning — Q1 2026
Managed by: Priya Sharma, VP Engineering ¦ Sprint Duration: 2 weeks
Sprint | Start Date | End Date | Team | Available Engineers | Capacity (Story Points) | Planned Points | Committed Features | Velocity (Actual) | Carry Over Points | Notes
Sprint 1 | Jan 6 2026 | Jan 17 2026 | AI/ML | 6 | 78 | 72 | Lead Scoring data pipeline + model training setup | 68 | 4 | Holiday ramp-up. 2 engineers onboarding.
Sprint 1 | Jan 6 2026 | Jan 17 2026 | Platform | 8 | 104 | 98 | Data API v2 final testing + migration tools | 102 | 0 | Strong sprint. API v2 on track.
Sprint 1 | Jan 6 2026 | Jan 17 2026 | Product-Sales | 4 | 52 | 48 | Lead Scoring UI - score badge + detail page | 45 | 3 | Design iteration needed on badge colors.
Sprint 1 | Jan 6 2026 | Jan 17 2026 | Product-Support | 5 | 65 | 60 | Unified Inbox Twitter integration | 58 | 2 | Twitter API v2 migration smoother than expected.
Sprint 1 | Jan 6 2026 | Jan 17 2026 | Security | 2 | 26 | 24 | SSO/SAML implementation | 22 | 2 | SAML edge cases with Okta.
Sprint 2 | Jan 20 2026 | Jan 31 2026 | AI/ML | 6 | 78 | 76 | Lead Scoring real-time inference API + batch scoring | 74 | 2 | Latency optimization ongoing.
Sprint 2 | Jan 20 2026 | Jan 31 2026 | Platform | 8 | 104 | 100 | Data API v2 launch + monitoring + docs | 96 | 4 | Launch day Jan 31. Pagination bug found.
Sprint 2 | Jan 20 2026 | Jan 31 2026 | Product-Sales | 4 | 52 | 50 | Lead Scoring list view + mobile display | 48 | 2 | Mobile design not finalized yet.
Sprint 2 | Jan 20 2026 | Jan 31 2026 | Product-Support | 5 | 65 | 62 | Unified Inbox WhatsApp integration | 55 | 7 | WhatsApp Business API setup slower than estimated.
Sprint 2 | Jan 20 2026 | Jan 31 2026 | Security | 2 | 26 | 26 | SSO/SAML GA + SOC 2 prep | 24 | 2 | SSO shipped Jan 30.
Sprint 3 | Feb 3 2026 | Feb 14 2026 | AI/ML | 6 | 78 | 78 | Lead Scoring SHAP explainability + admin config | TBD | TBD | Current sprint in progress.
Sprint 3 | Feb 3 2026 | Feb 14 2026 | Platform | 8 | 104 | 80 | Dashboard Builder - widget rendering engine | TBD | TBD | Team split: 3 on API v2 maintenance + 5 on dashboards.
Sprint 3 | Feb 3 2026 | Feb 14 2026 | Product-Sales | 4 | 52 | 50 | Dashboard Builder - drag and drop grid system | TBD | TBD | Working with Aisha on UX.
Sprint 3 | Feb 3 2026 | Feb 14 2026 | Product-Support | 5 | 65 | 65 | Unified Inbox Facebook + Instagram (Meta webhooks) | TBD | TBD | Pivoted from polling to webhooks. Extra effort.
Sprint 3 | Feb 3 2026 | Feb 14 2026 | Security | 2 | 26 | 26 | SOC 2 remediation (logging + MFA) | TBD | TBD | 2 findings from Deloitte audit.
Sprint 4 | Feb 17 2026 | Feb 28 2026 | AI/ML | 6 | 78 | 75 | Lead Scoring load testing + beta onboarding | Planned | N/A | Beta customer data migration support.
Sprint 4 | Feb 17 2026 | Feb 28 2026 | Platform | 8 | 104 | 96 | Dashboard Builder - data query layer + filters | Planned | N/A | Complex query optimization needed.
Sprint 4 | Feb 17 2026 | Feb 28 2026 | Product-Sales | 4 | 52 | 48 | Dashboard Builder - sharing and permissions | Planned | N/A | Depends on security permissions update (Feb 22).
Sprint 4 | Feb 17 2026 | Feb 28 2026 | Product-Support | 5 | 65 | 60 | Unified Inbox SMS + deduplication engine | Planned | N/A | Twilio SMS integration is straightforward.
Sprint 4 | Feb 17 2026 | Feb 28 2026 | Security | 2 | 26 | 20 | SOC 2 final prep + permissions framework update | Planned | N/A | Permissions update needed by Dashboard team.