Meeting Notes: Product Strategy — AI Lead Scoring Architecture

Date: November 3, 2025 (Monday) | 2:00 PM - 3:30 PM IST

Location: Conference Room B / Zoom

Attendees: Sarah Chen (PM), Marcus Webb (CTO), Priya Sharma (VP Eng), Rachel Torres (Head of DS), David Kim (VP Sales)

Note-taker: Sarah Chen

Agenda

AI Lead Scoring — real-time vs batch architecture decision

Data requirements and model selection

Timeline and resourcing

Beta customer strategy

Discussion Notes

1. Real-time vs Batch Scoring

Sarah presented three architecture options:

Option A: Pure real-time — Score on every lead creation/update. Full model inference per event.

Pro: Instant scores. Best UX.

Con: $0.12/score at scale. At 500K leads/month across customers = $60K/month compute.

Option B: Batch (hourly) — Score all leads every hour.

Pro: Cost-efficient ($0.02/score). Simple architecture.

Con: 68% of enterprise customers respond to hot leads within 1 hour (from our research). Hourly batch means we're already too late.

Option C: Hybrid — Lightweight model for instant scoring on creation; full model re-score every 4 hours.

Pro: Balance of speed and cost ($0.03/score average).

Con: Two models to maintain. Slight complexity.

Marcus raised concern about maintaining two models. Rachel confirmed her team can manage it — the lightweight model is a logistic regression that updates with the same training pipeline.

David strongly advocated for real-time: "Our biggest Enterprise prospect, TechFlow, told me last week that they respond to hot leads in 15 minutes. If we can't score in real-time, we're dead in the water for Enterprise."

Priya provided cost analysis: Hybrid approach at projected scale (Year 1: 200 customers, 100K leads/month) = $3K/month compute. Affordable.

DECISION: Option C — Hybrid approach

Instant scoring via lightweight model on lead creation (< 200ms)

Full model re-score every 4 hours

Confidence flag on instant score (if lightweight model confidence < 70%, flag for immediate full-model scoring)

All stakeholders aligned.

2. Model Selection

Rachel recommended XGBoost ensemble over deep learning:

Interpretability: SHAP values work natively with tree-based models

Training speed: 10x faster training cycle

Data efficiency: Performs well with 500 leads (vs. 10K+ for neural nets)

Customer onboarding: New customers get a working model faster

Marcus asked about future-proofing. Rachel confirmed the scoring API is model-agnostic — we can swap in a deep learning model later without changing the product surface.

DECISION: XGBoost ensemble with SHAP explainability

Rachel's commitment: Model prototype with 0.85+ AUC by December 15, 2025

3. Timeline

Priya proposed 8-sprint plan (16 weeks):

Sprints 1-3: Data pipeline + model training infrastructure

Sprints 4-5: Real-time scoring API + lightweight model

Sprint 6: UI (score display, explainability panel)

Sprint 7: Admin configuration

Sprint 8: Load testing + beta launch

Sarah flagged that Data API v2 (Raj's team) is a dependency for the data pipeline. Raj confirmed v2 ships January 31 — no conflict.

DECISION: Target March 15 for beta launch with 20 Enterprise customers

4. Beta Customer Strategy

David proposed focusing on customers who:

Have 500+ leads in system (model training minimum)

Currently use third-party scoring (proves willingness to adopt)

Have a strong PM/admin champion

Sarah will work with David to create shortlist by February 1.

ACTION ITEM: David to send list of top 30 Enterprise accounts for beta consideration by November 15.

Action Items

| Action | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Finalize hybrid architecture design doc | Priya Sharma | Nov 15 | Complete |
| Model prototype with AUC >= 0.85 | Rachel Torres | Dec 15 | Complete (AUC: 0.87) |
| Beta customer shortlist (30 accounts) | David Kim | Nov 15 | Complete |
| PRD v1 draft | Sarah Chen | Nov 30 | Complete |
| Data pipeline integration with API v2 | ML Team | Jan 31 | In Progress |

Next Meeting

November 17, 2025 — Design review for scoring UI with Lisa Park